## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations and Prerequistes for doing the project |  |  |  | 3- Completed
|  | 2 | Project Understanding, Setup, project achitecture and Google sheet Integration |  |  |  | 3- Completed
|  | 3 | Social Media Integration, Content Creation, Optimization |  |  |  | 3- Completed
|  | 4 | Sentiment Analysis, Slack Integration and deployment |  |  |  | 2- In Progress
Note on F1: ====== ID#AAABs4-wLUs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
du
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundation and prerequistes for doing the project | 23rd Sep | 7th Oct | K.DHANUSH | Learnt python basics for the Project | Done |  | Introduction | Learned Python and Jupyter Notebook Installation | Learned Naming Conventions in Python | Learned Data Types in Python | Practiced basic programs for better understanding | Practiced different data types and practiced examples | Learned Flow Controls in python | Learned Strings in python | Revised Flow Controls clearly | Practiced Strings in python like creating,accessing,etc... | Revised Strings and started Functions Topic | Practiced types of Functions clearly | Practiced Example programmes on all the topics which are covered | Learned Functions clearly
2 |  | Project Understanding, Setup, project achitecture and Google sheet Integration | 8th Oct | 22nd Oct | K.DHANUSH | Understood Project goals,setup, and architecture structure and Google Sheet Integration | Done |  | Understood about OOPs | Understood Packages in python | Understood About NLP Introduction and Text Handling | Understood SPACY Libraries | Practiced what the SPACY Libraries clearly | Understood about Project | Gave explination about project | Understood how to Install Virtual Environment | Understood about Hugging face Transformers | I Explained what I understood about the project | Practiced Hugging Face Transformers | Practiced OOPs concept | Revised NLP clearly | Done with google sheet integration
3 |  | Social Media Integration, Content Creation, Optimization | 23rd Oct | 6th Nov | K.DHANUSH | Learned social media API integration and effective content generation techniques | Done |  | Understood API Integration with twitter | Hands on Twitter API Integration | Collected API keys for Instagram and Facebook | Collected API keys and tokens in linkedin | Revision and Interactive session | Practiced API Integration | Understood about Mock Data Generation | Understood about how to Create content and Groq API | Understood about gsheet_connector | Understood about LLM | Revised LLM | Interactive Session | Understood about How to generate different versions of Content | Practiced different content generations
4 |  | Sentiment Analysis, Slack Integration and deployment | 6th Nov | 20th Nov | K.DHANUSH | Learned Sentiment Analysis, Slack Integration and deployment on streamlit | Done |  | Learnt about Application Programming Interface | Clearly understood about API | Revised API topic clearly | Worked on assignment | Interactive session | Understood about Content Optimization | Understood about Sentiment Analysis | Understood about Slack Integration | Understood about A/B testing | Revised A/B testing | Revised and Practiced Sentiment Analysis | Understood about Project Workflow | Discussed about Project Presentation | Mock presentation
Note on D2: ====== ID#AAABs4-wLUI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs4-wLVM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs4-wLUM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs4-wLUY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs4-wLU8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs4-wLUw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs4-wLU0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs4-wLVA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs4-wLUU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs4-wLUc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs4-wLUg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs4-wLUk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs4-wLVE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs4-wLUo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs4-wLVI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs4-wLUQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs4-wLU4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7